## Product Backlog
Definition of Done: |  | Development is completed and committed
All unit tests are run and pass
QA is completed and passes
Epic | Feature |  | Story | Description | Points | Notes
MVP | Schedule Appointment |  | Display Available Appointments | As A Patient I Want to see a list of available appointments So That I can select an appointment that meets my schedule
MVP | Schedule Appointment |  | Display Available Appointments - DB/API - Get Appointments | As A Scheduling System I Want to retrieve a list of available appointments So That I can display those appointments to the Patient | 8 | Database/API External - Team B
MVP | Schedule Appointment |  | Display Available Appointments - UI | As A Patient I Want to see a list of available appointments So That I can select an appointment that meets my schedule | 5
MVP | Schedule Appointment |  | Filter Type of Appointment | As A Patient I Want to filter available appointments by Type So That I can schedule the type of appointment that I need
MVP | Schedule Appointment |  | Filter Type of Appointment - DB/API - Get Appointment Types | As A Scheduling System I Want to retrieve all appointment types So That the Patient can filter available appointments by Type | 5 | Database/API External - Team B
MVP | Schedule Appointment |  | Filter Type of Appointment - DB/API - Filter Appointments | As A Scheduling System I Want to retrieve appointments filtered by Type So That the Patient can select an appointment that's for a specific Type | 5 | Database/API External - Team B
MVP | Schedule Appointment |  | Filter Type of Appointment - UI | As A Patient I Want to filter available appointments by Type So That I can schedule the type of appointment that I need | 3
MVP | Schedule Appointment |  | Filter Available Times by AM/PM | As A Patient I Want to filter available appointments by AM/PM So That I can schedule an appointment that meets my schedule
MVP | Schedule Appointment |  | Filter Available Times by AM/PM - DB/API - Filter Appointments | As A Scheduling System I Want to retrieve appointments filtered by AM/PM So That the Patient can select an appointment that's in the AM or PM | 5 | Database/API External - Team B
MVP | Schedule Appointment |  | Filter Available Times by AM/PM - UI | As A Patient I Want to filter available appointments by AM/PM So That I can schedule an appointment that meets my schedule | 3
MVP | Schedule Appointment |  | Contact Information | As A Patient I Want to enter my contact information So That my contact information can be associated with the appointment I'm scheduling
MVP | Schedule Appointment |  | Contact Information - DB/API - Save Contact Information | As A Scheduling System I Want to save the Patient's contact information So That I can associate the Patient's contact information with an appointment | 5 | Database/API External - Team B
MVP | Schedule Appointment |  | Contact Information - UI | As A Patient I Want to enter my contact information So That my contact information can be associated with the appointment I'm scheduling | 3
MVP | Schedule Appointment |  | Appointment Code Generation | As A Scheduling System I Want to generate an Appointment Code So That I can retrieve or update the scheduled appointment | 5 | Database/API External - Team B
MVP | Appointment Confirmation |  | Send Confirmation Email | As A Patient I Want Enter my email So That I can confirm that my appointment was set
MVP | Appointment Confirmation |  | Send Confirmation Email DB/API - Get Email | As A Confirmation Email I Want send a confirmation email to the patient's email that was entered So That my patient can confirm that their appointment was set | 3 | Database/API External - Team B
MVP | Appointment Confirmation |  | Send Confirmation Email - UI | As A Patient I Want to see and interact with the Confirmation Email text box So That I can enter my email to have the confirmation email sent to my email | 5
MVP | Appointment Confirmation |  | Send Confirmation Text | As A Patient I Want to enter my phone number So That I can have my confirmation text sent to my phone number
MVP | Appointment Confirmation |  | Send Confirmation Text DB/API - Get Phone Number | As A Confirmation Text I Want retrieve the patient's Phone Number So That I can send them a Confirmation Text | 3 | Database/API External - Team B
MVP | Appointment Confirmation |  | Send Confirmation Text - UI | As A Patient I Want to see and interact with the Confirmation Text text box So That I can enter my phone number to have the Confirmation Text sent to my phone number in SMS/Messages | 5
MVP | Device Calendar |  | Send Appointment to Device Calendar | As I patient I want to add the appointment to calendar so that it allows me to set reminder before appointment. For example, I can receive a notification a day before, an hour before, or even just a few minutes prior to your appointment, ensuring that I don’t forget
MVP | Appointment Reminder |  | Send Reminder Email | As I patient I want to receive a reminder email ahead of my appointment (typically a day or a few hours before) so that I have enough time to prepare, make arrangements, and avoid missing an appointment.
MVP | Appointment Reminder |  | Send Reminder Text | As a patient I want to receive text reminders so that it helps me to prepare in advance whether it’s a day before, a few hours ahead, or even right before my appointment.
| View Appointment |  | Display Appointment via Text | As A Patient I Want to be brought to my appointment page via Text So That I can view my appointment
| View Appointment |  | Display Appointment via Text DB/API - Bring Patient to Appointment Page | As A Scheduling System I Want to retrieve a scheduled appointment So That my patient can view their appointment | 3 | Database/API External - Team B
| View Appointment |  | Display Appointment via Text - UI | As A Patient I Want to be brought to my appointment page via Text So That I can view my appointment | 5
| View Appointment |  | Display Appointment via Email | As A Patient I Want to be brought to my appointment page via Email So That I can view my appointment
| View Appointment |  | Display Appointment via Email DB/API - Bring Patient to Appointment Page | As A Scheduing System I Want to retrieve a scheduled appointment So That my patient can view their appointment | 3 | Database/API External - Team B
| View Appointment |  | Display Appointment via Email - UI | As A Patient I Want to be brought to my appointment page via Email So That I can view my appointment | 5
| Search Appointment |  | Search Appointment | As A Patient I Want to search for my appointment via Appointment Code So That I can view a scheduled appointment
| Search Appointment |  | Search Appointment - DB/API - Retrieve Appointment | As A Scheduling System I Want to retrieve an appointment from the database via Appointment Code So That my patient can view their appointment | 8 | Database/API External - Team B
| Search Appointment |  | Search Appointment - UI | As A Patient I Want to search for my appointment via Appointment Code So That I can view a scheduled appointment | 3

## Sprint Planning
Team A - Dentist Appointment Scheduling Website
Product Owner: |  | Anton Andrews
Scrum Master: |  | Ashton Andrews
Developers: |  | Mukesh Mahato
Carl Abbott
Est. Capacity: |  | 40 Points
Sprint 1 - 11/26/24 to 12/09/24
Epic |  | Feature | Story | Description | Points | Notes
MVP | Schedule Appointment |  | Display Available Appointments - DB/API - Get Appointments | As A Scheduling System I Want to retrieve a list of available appointments So That I can display those appointments to the Patient | 8 | Database/API External - Team B
MVP | Schedule Appointment |  | Display Available Appointments - UI | As A Patient I Want to see a list of available appointments So That I can select an appointment that meets my schedule | 5
MVP | Schedule Appointment |  | Filter Type of Appointment - DB/API - Get Appointment Types | As A Scheduling System I Want to retrieve all appointment types So That the Patient can filter available appointments by Type | 5 | Database/API External - Team B
MVP | Schedule Appointment |  | Filter Type of Appointment - DB/API - Filter Appointments | As A Scheduling System I Want to retrieve appointments filtered by Type So That the Patient can select an appointment that's for a specific Type | 5 | Database/API External - Team B
MVP | Schedule Appointment |  | Filter Type of Appointment - UI | As A Patient I Want to filter available appointments by Type So That I can schedule the type of appointment that I need | 3
MVP | Schedule Appointment |  | Filter Available Times by AM/PM - DB/API - Filter Appointments | As A Scheduling System I Want to retrieve appointments filtered by AM/PM So That the Patient can select an appointment that's in the AM or PM | 5 | Database/API External - Team B
MVP | Schedule Appointment |  | Filter Available Times by AM/PM - UI | As A Patient I Want to filter available appointments by AM/PM So That I can schedule an appointment that meets my schedule | 3
MVP | Schedule Appointment |  | Contact Information - DB/API - Save Contact Information | As A Scheduling System I Want to save the Patient's contact information So That I can associate the Patient's contact information with an appointment | 5 | Database/API External - Team B
39

## Sprint 1 Review
Team A - Dentist Appointment Scheduling Website
Product Owner: |  | Anton Andrews
Scrum Master: |  | Ashton Andrews
Developers: |  | Mukesh Mahato
Carl Abbott
Est. Points: |  | 39 Points
Completed Points: |  | 34 Points
Sprint 1 - 11/26/24 to 12/09/24
Epic |  | Feature | Story | Description | Not Started | Complete | Notes
MVP | Schedule Appointment |  | Display Available Appointments - DB/API - Get Appointments | As A Scheduling System I Want to retrieve a list of available appointments So That I can display those appointments to the Patient |  | 8 | Database/API External - Team B
MVP | Schedule Appointment |  | Display Available Appointments - UI | As A Patient I Want to see a list of available appointments So That I can select an appointment that meets my schedule |  | 5
MVP | Schedule Appointment |  | Filter Type of Appointment - DB/API - Get Appointment Types | As A Scheduling System I Want to retrieve all appointment types So That the Patient can filter available appointments by Type |  | 5 | Database/API External - Team B
MVP | Schedule Appointment |  | Filter Type of Appointment - DB/API - Filter Appointments | As A Scheduling System I Want to retrieve appointments filtered by Type So That the Patient can select an appointment that's for a specific Type |  | 5 | Database/API External - Team B
MVP | Schedule Appointment |  | Filter Type of Appointment - UI | As A Patient I Want to filter available appointments by Type So That I can schedule the type of appointment that I need |  | 3
MVP | Schedule Appointment |  | Filter Available Times by AM/PM - DB/API - Filter Appointments | As A Scheduling System I Want to retrieve appointments filtered by AM/PM So That the Patient can select an appointment that's in the AM or PM |  | 5 | Database/API External - Team B
MVP | Schedule Appointment |  | Filter Available Times by AM/PM - UI | As A Patient I Want to filter available appointments by AM/PM So That I can schedule an appointment that meets my schedule |  | 3
MVP | Schedule Appointment |  | Contact Information - DB/API - Save Contact Information | As A Scheduling System I Want to save the Patient's contact information So That I can associate the Patient's contact information with an appointment | 5 |  | Database/API External - Team B
[5 empty] | 5 | 34